## Wallstreetmojo.com
Project Timeline Template
Prepared by Dheeraj Vaidya, CFA, FRM
dheeraj@wallstreetmojo.com
visit - www.wallstreetmojo.com

## Project Timeline Template
Completed
Project Name: | ……………………………. | Start Date: | ……………………….. |  | Duration: | ………………
Project Manager Name: | ……………………………. | End Date: | ………………………..
CATEGORY | TASK | Status | START | END | Duration |  | Hold
Basement Build | Excavation | Completed | 2020-01-01 | 2020-01-15 | 14 |  | In Progress
| Digging | Completed | 2020-01-15 | 2020-02-05 | 21 |  | Not Started
| Water pipeline | Completed | 2020-02-06 | 2020-02-26 | 20
| Underground Parking | Hold | 2020-01-20 | 2020-03-01 | 41
Building Setup | Construction | In Progress | 2020-02-01 | 2020-02-15 | 14
| Electric Installation | Not Started | 2020-02-05 | 2020-02-22 | 17
| Safety Features | Not Started | 2020-02-23 | 2020-03-05 | 11
| Water Setup | Not Started | 2020-03-06 | 2020-03-09 | 3
Painting | Raw Material | Not Started | 2020-03-10 | 2020-04-09 | 30
| First level paint | Not Started | 2020-03-10 | 2020-03-20 | 10
| Second level paint | Not Started | 2020-03-20 | 2020-04-09 | 20
| Final level paint | Not Started | 2020-04-10 | 2020-04-15 | 5
AC Installation | AC Unit purchase | Not Started | 2020-03-20 | 2020-04-04 | 15
| Outdoor setup | Not Started | 2020-03-20 | 2020-04-19 | 30
| Indoor setup | Not Started | 2020-04-05 | 2020-04-20 | 15
Parking setup | Land Levelling | Not Started | 2020-04-21 | 2020-04-26 | 5
| Marking | Not Started | 2020-04-21 | 2020-05-02 | 11
| CC Tv Setup | Not Started | 2020-05-03 | 2020-05-03 | 0
Handover | Final Inspection | Not Started | 2020-01-01 | 2020-02-28 | 58
| House keeping | Not Started | 2020-01-01 | 2020-04-19 | 109
| Wrapup | Not Started | 2020-03-01 | 2020-04-29 | 59